## 2016.02.01
Item | Task |  | Finished % | Risk (including technologies,resource, management, communications,.., etc.) | Risk Feedback (Record) | Labor/hr. (工時, base on 8 hrs/d)
| Project Name / Platform | Task description
1. In process this week | Please fill in: " Internal study / Platform(ex. Android-4.4, Android-5.0 ,Intel-SoFIA,Linux,..,etc.)" or "Internal study" if the case is internal study instead of a project. |  |  | (Please fill in the tough issues or risks in here)
Inernal study
MAX+
MAX1\X1
S2
| Picasso | RF driver porting – based on truth table 1. Verification with Nathan: 目前PICASSO真值表，已與Nathan一起驗證，確認無誤。 但是目前真值表還不是最後final 的版本，待明豐提供最新的真值表for ANT使用， 會再幫忙修改code，並與他一起驗證。 Note: 之前 GSM, TD-SCDMA and CDMA 因為沒有 Aux 線路, 所以無法拉 High, 這部分是正確的. 2. 預計下星期板子才會回來. | 65%
Zion
2. Going to do next week | Pleasea fill in: " Internal study / Platform(ex. Android-4.4, Android-5.0 ,Intel-SoFIA,Linux,..,etc.)" or "Internal study" if the case is internal study instead of a project.
Inernal study
MAX+
S2
| Picasso | RF driver porting – based on truth table Verification\Debug with RF Nathan
Zion
3. Is there any expected uncertainties or risks in coming week or month ? | Pleasea fill in: " Internal study / Platform(ex. Android-4.4, Android-5.0 ,Intel-SoFIA,Linux,..,etc.)" or "Internal study" if the case is internal study instead of a project.

## 2016.01.25
Item | Task |  | Finished % | Risk (including technologies,resource, management, communications,.., etc.) | Risk Feedback (Record) | Labor/hr. (工時, base on 8 hrs/d)
| Project Name / Platform | Task description
1. In process this week | Please fill in: " Internal study / Platform(ex. Android-4.4, Android-5.0 ,Intel-SoFIA,Linux,..,etc.)" or "Internal study" if the case is internal study instead of a project. |  |  | (Please fill in the tough issues or risks in here)
Inernal study
MAX+
MAX1\X1
| X5 | ET(Envelope tracker) Calibration: compare X5 RF with max_plus\X2
| Picasso | RF driver porting – based on truth table 1. Verification with Nathan: (因為板子還沒回來, 先直接量 GPIO 的電壓, 1.8V 為High, 0V 為Low) WCDMA and LTE are almost PASS. 2. Porting new truth table: RF MF provided new truth table(1/20). Note: 預計下星期板子才會回來. | 65%
Zion
2. Going to do next week | Pleasea fill in: " Internal study / Platform(ex. Android-4.4, Android-5.0 ,Intel-SoFIA,Linux,..,etc.)" or "Internal study" if the case is internal study instead of a project.
Inernal study
MAX+
| X5 | ET Calibration
| Picasso | RF driver porting – based on truth table Verification\Debug with RF Nathan
Zion
3. Is there any expected uncertainties or risks in coming week or month ? | Pleasea fill in: " Internal study / Platform(ex. Android-4.4, Android-5.0 ,Intel-SoFIA,Linux,..,etc.)" or "Internal study" if the case is internal study instead of a project.

## 2016.01.18
Item | Task |  | Finished % | Risk (including technologies,resource, management, communications,.., etc.) | Risk Feedback (Record) | Labor/hr. (工時, base on 8 hrs/d)
| Project Name / Platform | Task description
1. In process this week | Please fill in: " Internal study / Platform(ex. Android-4.4, Android-5.0 ,Intel-SoFIA,Linux,..,etc.)" or "Internal study" if the case is internal study instead of a project. |  |  | (Please fill in the tough issues or risks in here)
Inernal study
MAX+
MAX1\X1
SR1
| Picasso | RF driver porting – based on truth table 1. Remove DPDT. 2. Change Tuner QFE2550 to RF1119 for Main Antenna. 3. Add RF1119 for Aux Antenna 4. Rat porting: GSM, WCDMA, FDD-LTE, TDD-LTE, TD-SCDMA, CDMA. 5. Verification\Debug with RF Nathan | 50%
Zion
2. Going to do next week | Pleasea fill in: " Internal study / Platform(ex. Android-4.4, Android-5.0 ,Intel-SoFIA,Linux,..,etc.)" or "Internal study" if the case is internal study instead of a project.
Inernal study
MAX+
SR1
| Picasso | RF driver porting – based on truth table 1. Remove DPDT. 2. Change Tuner QFE2550 to RF1119 for Main Antenna. 3. Add RF1119 for Aux Antenna 4. Rat porting: GSM, WCDMA, FDD-LTE, TDD-LTE, TD-SCDMA, CDMA. 5. Verification\Debug with RF Nathan\Pandy
Zion
3. Is there any expected uncertainties or risks in coming week or month ? | Pleasea fill in: " Internal study / Platform(ex. Android-4.4, Android-5.0 ,Intel-SoFIA,Linux,..,etc.)" or "Internal study" if the case is internal study instead of a project.

## 2016.01.11
Item | Task |  | Finished % | Risk (including technologies,resource, management, communications,.., etc.) | Risk Feedback (Record) | Labor/hr. (工時, base on 8 hrs/d)
| Project Name / Platform | Task description
1. In process this week | Please fill in: " Internal study / Platform(ex. Android-4.4, Android-5.0 ,Intel-SoFIA,Linux,..,etc.)" or "Internal study" if the case is internal study instead of a project. |  |  | (Please fill in the tough issues or risks in here)
Inernal study
MAX+
MAX1\X1
SR1
| Picasso | Antenna switch porting Remove DPDT. Replace Tuner(QFE2550) with RF1119 for main antenna. Add RF1119 for Aun antenna. Rat porting for GSM, WCDAM, CDMA, TD-SCDMA, LTE. Debug with RF team. | 30%
Zion
2. Going to do next week | Pleasea fill in: " Internal study / Platform(ex. Android-4.4, Android-5.0 ,Intel-SoFIA,Linux,..,etc.)" or "Internal study" if the case is internal study instead of a project.
Inernal study
MAX+
SR1
| Picasso | Antenna switch porting Remove DPDT Replace Tuner(QFE2550) with RF1119 for main antenna. Add RF1119 for Aun antenna. Rat porting for GSM, WCDAM, CDMA, TD-SCDMA, LTE. Debug with RF team.
Zion
3. Is there any expected uncertainties or risks in coming week or month ? | Pleasea fill in: " Internal study / Platform(ex. Android-4.4, Android-5.0 ,Intel-SoFIA,Linux,..,etc.)" or "Internal study" if the case is internal study instead of a project.